## Summary
2017-10-19
Courses On Hold | 1
No Storyboard Yet | 133
Storyboard in Progress | 2
Storyboard Complete | 0
Storyline in Progress | 1
Published Courses | 99
Total Roadmap | 236
Completed SMB Storyboards | 82
Completed SMB Documentation | #REF!
KOD In Progress | #REF!
KOD Complete | #REF!

## Roadmap
Topic(s) | Category | Subcategory | TOD Course Name | Count | Course # | Status | Publish Date Creation Date | Projected Completion Date | Days Out for Approval | Analysis Req'd | Rating | Resources/Notes | Priority
Moving Around in BisTrack, Finding Documents and Work | BisTrack Basics | Overview | BisTrack Navigation | 1 | BT100 | Published | 2016-06-21 |  |  |  |  | SMB
Finding Customers and Suppliers | BisTrack Basics | Overview | Customers and Suppliers Overview | 2 | BT101 | Published | 2016-06-27 |  |  |  |  | SMB
Finding Products | BisTrack Basics | Overview | Products Overview | 3 | BT102 | Published | 2016-06-22 |  |  |  |  | SMB
Basic Sales Order, Sales Order Cycle, Finding Sales Documents | BisTrack Basics | Overview | Sales Orders Overview | 4 | BT103 | Published | 2016-07-11 |  |  |  |  | SMB
Basic Purchase Order | BisTrack Basics | Overview | Purchase Orders Overview | 5 | BT104 | Published | 2016-07-13 |  |  |  |  | SMB
Sales Tax - Setup | BisTrack Basics | Overview | Sales Tax Overview | 6 | BT105 | Published | 2016-08-29 |  |  |  |  | SMB
Sales Tax - On a sales order, Sales Tax - On a credit note, Sales Tax - Working Examples, Sales Tax - Fixing tax errors, Sales Tax - Reports | BisTrack Basics | Using | Using Sales Tax | 7 | BT106 | Published | 2016-09-12 |  |  |  |  | SMB
Users, User Groups, User Permissions | System Manager | Overview | Users Overview | 8 | BT107 | Published | 2016-09-12 |  |  |  |  | SMB
Reason Codes | System Manager | Setup | Reason Codes | 9 | BT108 | Published | 2016-08-22 |  |  |  |  | SMB
Entering a Quick (Collect Now) Sale - Account, Entering a Will Call (Collect Later) Sale - Account, Entering a Delivered Sale - Account, Entering a Quick (Collect Now) Sale - Cash, Entering a Will Call (Collect Later) Sale - Cash | Sales | Transactions | Using Sales Orders | 10 | BT109 | Published | 2016-07-25 |  |  |  |  | SMB
Cash Drawer Balancing - Overview, Cash Drawer Balancing - Cash Details and Lodgements, Cash Drawer Balancing - Reports and Closing | Sales | Overview | Cash Drawer Balancing | 11 | BT110 | Published | 2016-08-16 |  |  |  |  | SMB
Special Order Items - Overview, Special Order Items - Setup | Sales | Overview | Special Order Items Overview | 12 | BT111 | Published | 2016-07-26 |  |  |  |  | SMB
Special Order Items on a Sales Document, Special Order Item on a Purchase Order | Sales | Using | Using Special Order Items | 13 | BT112 | Published | 2016-08-12 |  |  |  |  | SMB
Direct Order - Overview, Direct Order - Process | Sales | Overview | Direct Order Overview | 14 | BT113 | Published | 2016-09-21 |  |  |  |  | SMB
Quotes | Sales | Tansactions | Using Quotes | 15 | BT114 | Published | 2016-08-18 |  |  |  |  | SMB
Credit Note/Cash Refund from Invoice, Credit Note/Cash Refund without Invoice, Credit Note/Cash Refund with New Sale, Credit Note/Cash Refund Additional Options, Cash Refund from Invoice, Cash Refund without Invoice, Credit Note Browser | Sales | Transactions | Using Credit Notes | 16 | BT115 | Published | 2016-08-18 |  |  |  |  | SMB
Cash Refunds and Company Checks - Overview and Setup [Great Plains], Cash Refunds and Company Checks - Process [Great Plains] | Sales | Transactions | Issuing Company Checks for Refunds | 17 | BT116 | Published | 2016-08-17
Invoice from within Order Monitor, Auto Invoice Orders, Invoice Generator, Invoice Browser | Sales | Overview | Invoicing Overview | 18 | BT117 | Published | 2016-08-30 |  |  |  |  | SMB
Invoice Cost Adjustment, Invoice Tax Adjustment | Sales | Transactions | Invoiceing Adjustments | 19 | BT118 | Published | 2016-08-22 |  |  |  |  | SMB
Addresses and Job Accounts, Customer Contacts, Customer Groups, Customer Payment Terms, Customer Tax Codes, Customer Tax Codes, Customer Types | Customers | Setup | Customer Accounts Overview | 20 | BT119 | Published | 2016-09-08 |  |  |  |  | SMB
Adding a New Customer | Customers | Setup | Adding New Customer Accounts | 21 | BT120 | Published | 2016-09-09 |  |  |  |  | SMB
Credit Control Statuses and Credit Ratings, Managing Customer Accounts | Customers | Maintenance | Maintaining Customer Accounts | 22 | BT121 | Published | 2016-09-12 |  |  |  |  | SMB
Credit Controls - Overview and Setup, Credit Controls - Process | Customers | Overview | Credit Controls Overview | 23 | BT122 | Published | 2016-09-13 |  |  |  |  | SMB
Payments on Account (Back Office), Payments on Account (at POS) | Accounts Receivable | Using | Taking Payments on Account | 24 | BT123 | Published | 2016-09-19 |  |  |  |  | SMB
Cash Matching - Cash Matching Browser, Cash Matching - Process, Cash Matching - Customer's with Job Accounts, Cash Matching - Applying Credits, Cash Matching - Direct Postings, Cash Matching - Miscellaneous Functions | Accounts Receivable | Using | Using the Cash Matching Process | 25 | BT124 | Published | 2016-09-20 |  |  |  |  | SMB
Cash Matching - Cash Matching Browser, Cash Matching - Process, Cash Matching - Customer's with Job Accounts, Cash Matching - Applying Credits, Cash Matching - Direct Postings, Cash Matching - Miscellaneous Functions | Accounts Receivable | Using | Advanced Cash Matching | 26 | BT125 | Published | 2016-10-06 |  |  |  |  | SMB
Cash Matching - Cash Matching Browser, Cash Matching - Process, Cash Matching - Customer's with Job Accounts, Cash Matching - Applying Credits, Cash Matching - Direct Postings, Cash Matching - Miscellaneous Functions | Accounts Receivable | Using | Using Direct Posting | 27 | BT126 | Published | 2016-10-06 |  |  |  |  | SMB
NSF Payments | Accounts Receivable | Transactions | Managing NSF Payments | 28 | BT127 | Published | 2016-09-23 |  |  |  |  | SMB
Finance Charges - Overview and Setup, Finance Charges - Generate | Accounts Receivable | Transactions | Finance Charges | 29 | BT128 | Published | 2016-09-22 |  |  |  |  | SMB
Statements - Overview and Setup, Statements - Generate | Accounts Receivable | Using | Generating Accounts Receivable Statements | 30 | BT129 | Published | 2016-09-28 |  |  |  |  | SMB
Adding a New Supplier, Supplier Addresses, Supplier Contacts, Supplier Groups, Supplier Payment Terms, Supplier Types | Suppliers | Setup | Setting Up New Suppliers | 31 | BT130 | Published | 2016-10-06 |  |  |  |  | SMB
Suppliers - Import Spreadsheet and Importing | Suppliers | Setup | Importing New Suppliers | 32 | BT131 | Hold | On Hold
Introducing Purchase Orders, Pricing Options, Text Lines, Line Notes and Other Tab, Options for Entering Qty and Price | Purchasing | Overview | Creating a Purchase Order | 33 | BT132 | Published | 2016-09-27 |  |  |  |  | SMB
Entering a Stock Purchase Order, Create New Product for Purchase Order, Generic Products on a Purchase Order, Lumber Products on a Purchase Order, Adding Products using 'Add to Selection Cart', Product Costs and Price Calculation Tab | Purchasing | Transactions | Using Purchase Orders | 34 | BT133 | Published | 2016-10-06 |  |  |  |  | SMB
Introducing Stock Receipts, Receive a Purchase Order in Full, Receive a Partial Purchase Order, Changing Costs on a Stock Receipt | Purchasing | Transactions | Creating Stock Receipts | 35 | BT134 | Published | 2016-10-10 |  |  |  |  | SMB
UOMs and UOM Rules. Product Groups, Adding a Generic Product, Adding a Generic Product (Multiple UOMs) | Products | Setup | Product Setup | 36 | BT135 | Published | 2016-10-06 |  |  |  |  | SMB
Adding a Lumber Product (Random Length Parent), Adding a Lumber Product (Each Length Child), Adding a Lumber Product (Random Length - Stocked Lengths), Adding a Lumber Product (Stocked Footage), Adding a Lumber Product (Random Length/Random Width), Adding a Lumber Product (Sheet Goods) | Products | Setup | Lumber Product Setup | 37 | BT136 | Published | 2016-10-12 |  |  |  |  | SMB
Print Labels | Prodcuts | Overview | Label Printing Overview | 38 | BT137 | Published | 2016-10-13 |  |  |  |  | SMB
Back Orders, Back Order Release | Sales | Using | Using Back Orders | 39 | BT138 | Published | 2016-11-16 |  |  |  |  | SMB
Stock Counts | Stock Management | Using | Using Stock Counting with Tickets | 40 | DCD879 | Published | 2017-08-30 |  |  |  |  | SMB
|  |  | Using Stock Counting with Count Sheets | 41 | DCD885 | Published | 2017-08-31 |  |  |  |  | SMB
Stock Counts | Stock Management | Overview | Stock Counting Overview | 42 | BT140 | Published | 2016-11-15 |  |  |  |  | SMB
Supplier Returns | Purchasing | Transactions | Supplier Returns | 43 | BT141 | Published | 2016-11-23 |  |  |  |  | SMB
Stock Invoices | Accounts Payable | Using | AP Invoices | 44 | BT142 | Published | 2017-04-05 |  |  |  |  | SMB
AP Invoices | Accounts Payable | Using | Using AP Invoice Options | 45 | DCD605 | Published | 2017-04-14 |  |  |  |  | SMB
Overhead Invoices | Accounts Payable | Using | Overhead, Add Cost and Direct Invoices | 46 | DCD606 | Published | 2017-04-24 |  |  |  |  | SMB
Supplier Credit Notes | Accounts Payable | Using | Supplier Credit Notes | 47 | BT147 | Published | 2017-02-21 |  |  |  |  | SMB
Product Price History/Stock Movement | Stock Management | Views | Product Price History/Stock Movement | 48 | BT143 | Published | 2017-02-28 |  |  |  |  | SMB
Stock Adjustments | Stock Management | Transactions | Stock Adjustments | 49 | BT144 | Published | 2016-11-11 |  |  |  |  | SMB
Stock Transfers | Stock Management | Transactions | Stock Transfers | 50 | BT145 | Published | 2017-01-31 |  |  |  |  | SMB
Introduction to the Epicor Learning Center Introduction to the Epicor Learning Center Desc.: This course will provide an overview of the Training on Demand Learning Center. You will be shown how to navigate within the Learning Management System (LMS) and customize the Home Page. We will address the use of Assignments and Transcripts as well as how to manage personal information including your password. We will also view and search the Course Catalog to find and complete courses. Level: Basic Length: 14 Minutes | Training on Demand | Administrators | Introduction to the Epicor Learning Center Introduction to the Epicor Learning Center Desc.: This course will provide an overview of the Training on Demand Learning Center. You will be shown how to navigate within the Learning Management System (LMS) and customize the Home Page. We will address the use of Assignments and Transcripts as well as how to manage personal information including your password. We will also view and search the Course Catalog to find and complete courses. Level: Basic Length: 14 Minutes | 51 | DCD541 | Published | 2016-11-17 |  |  |  |  | SMB
Creating and Tracking Assignments | Training on Demand | Administrators | Creating and Tracking Assignments | 52 | DCD545 | Published | 2017-02-24 |  |  |  |  | SMB
Creating Tasks, Accomplishments, Tests and Agendas | Training on Demand | Administrators | Creating Tasks, Accomplishments, Tests and Agendas | 53 | DCD546 | Published | 2017-02-28 |  |  |  |  | SMB
Customizing Your Epicor Learning Center Home Page | Training on Demand | Administrators | Customizing Your Epicor Learning Center Home Page | 54 | DCD544 | Published | 2017-02-24 |  |  |  |  | SMB
Epicor Learning Center Navigation for Administrators | Training on Demand | Administrators | Epicor Learning Center Navigation for Administrators | 55 | DCD542 | Published | 2017-02-09 |  |  |  |  | SMB
Epicor Learning Center User Accounts and Groups | Training on Demand | Administrators | Epicor Learning Center User Accounts and Groups | 56 | DCD543 | Published | 2017-02-24 |  |  |  |  | SMB
Price Negotiation Tab, Price Calculation Tab, History and Quotes, Pricing Options 1 (Lump sum pricing, manual price lines, negotiation discounts) | Sales | Using | Re-Pricing Prodcuts on Sales Documents | 57 | DCD625 | Published | 2017-05-04 |  |  |  |  | SMB
Price Negotiation Tab, Price Calculation Tab, History and Quotes, Pricing Options 1 (Lump sum pricing, manual price lines, negotiation discounts) | Sales | Using | Using Pricing Options | 58 | DCD632 | Published | 2017-05-02 |  |  |  |  | SMB
Consolidate Lines and Sections, Sections and Summary Lines | Sales | Using | Using Sections and Summary Lines | 59 | DCD631 | Published | 2017-05-09 |  |  |  |  | SMB
Manual Order Lines (SO) - Overview, Manual Order Lines (PO) - Setup, Manual Order Lines on a Sales Document, V | Sales | Tips & Tricks | Manual Order Line Types (MOLTs) Overview | 60 | DCD661 | Published | 2017-06-03 |  |  |  |  | SMB
Additional Cost Charges (SO) - Overview, Additional Cost Charges (PO) - Setup | Purchasing | Overview | Additional Cost/Charges Overview | 61 | DCD727 | Published | 2017-07-13 |  |  |  |  | SMB
Additional Cost Charges on a Sales Document, Additional Cost Charges on a Purchase Document | Purchasing | Transactions | Using Additional Cost/Charges | 62 | DCD779 | Published | 2017-07-13 |  |  |  |  | SMB
Stock Warnings - Overview and Handling Options | Sales | Overview | Stock Warnings Overview | 63 | DCD609 | Published | 2017-04-14 |  |  |  |  | SMB
Stock Warnings on a Sales Document | Sales | Using | Using Stock Warnings | 64 | DCD611 | Published | 2017-04-25 |  |  |  |  | SMB
Call Off Orders | Sales | Overview | Call Off Orders Overview | 65 | DCD846 | Published | 2017-08-28
Call Off Orders Schedules | Sales | Using | Using Call Off Order Schedules | 66 | DCD948 | Published | 2017-09-29
Added Value Operations - Overview, Added Value Operations - Setup | Sales | Overview | Added Value Operations (AVOs) Overview | 67 | DCD973 | Published | 2017-09-22
Added Value Operations on a Sales Document | Sales | Using | Using Added Value Operations on Sale Documents | 68 | DCD923 | Published | 2017-09-22
Customer Loyalty Programs - Overview, Customer Loyalty Programs - Setup | Sales | Overview | Customer Loyalty Programs Overview | 69 | DCD861 | Published | 2017-08-29
Customer Loyalty Programs - Process | Sales | Using | Using Customer Loyalty Programs | 70 | DCD866 | Published | 2017-09-07
Customer Loyalty Programs - Process | Sales | Using | Using Loyalty Coupons | 71 | DCD868 | Published | 2017-09-20
Introducing Order Monitor | Dispatch & Delivery | Overview | Order Monitor Overview | 72 | DCD700 | Published | 2017-06-15 |  |  |  |  | SMB
Using Order Monitor, Advanced Picking - orders for Delivery, Advanced Picking - orders for Collection, Batch Method for Processing Orders | Dispatch & Delivery | Using | Using Order Monitor | 73 | DCD699 | Published | 2017-06-30 |  |  |  |  | SMB
Introducing Dispatch and Delivery (aka Journey Planner ) | Dispatch & Delivery | Overview | Dispatch Delivery Overview | 74 | DCD703 | Published | 2017-06-09 |  |  |  |  | SMB
Delivery Areas, Times and Dates Required, Vehicles and Drivers - Setup, Preparing a Delivery | Dispatch & Delivery | Setup | Preparing for Dispatch Delivery | 75 | DCD706 | Published | 2017-07-06 |  |  |  |  | SMB
Dispatching a Delivery, Starting and Completing a Delivery, Additional Cost/Charge Proration on a Delivery, Delivery Planner Views, Dispatch and Delivery "My Options", Get Directions | Dispatch & Delivery | Using | Dispatching a Delivery | 76 | DCD709 | Published | 2017-07-12 |  |  |  |  | SMB
Dispatching a Delivery, Starting and Completing a Delivery, Additional Cost/Charge Proration on a Delivery, Delivery Planner Views, Dispatch and Delivery "My Options", Get Directions | Dispatch & Delivery | Using | Using Back Orders in Order Monitor | 77 | DCD700 | Published | 2017-07-13 |  |  |  |  | SMB
Adding additional Deposits or Payments | Sales | Using | Deposits and Payments | 78 | DCD689 | Published | 2017-05-24 |  |  |  |  | SMB
Counter Sales | Sales | Overview | Counter Sales Overview | 79 | DCD696 | Published | 2017-06-07 |  |  |  |  | SMB
Remove Elapsed Documents | Sales | Overview | Elapsed Documents Overview | 80 | DCD690 | Published | 2017-04-25 |  |  |  |  | SMB
Convert Quote to special pricing | Sales | Using | Using Quotes and Special Prices | 81 | DCD792 | Published | 2017-07-19 |  |  |  |  | SMB
Merging/Copying Pos | Purchasing | Transactions | Merging and Copying Pos | 82 | DCD722 | Published | 2017-07-13 |  |  |  |  | SMB
Selling Price Changes | Stock Management | Using | Using Selling Price Changes | 83 | DCD801 | Published | 2017-07-20 |  |  |  |  | SMB
Creating basic promotions | Pricing | Overview | Creating Promotions Overview | 84 | DCD802 | Published | 2017-07-20 |  |  |  |  | SMB
Notes, Special Instructions and Text Lines | Sales | Using | Using Notes, Special Instructions and Text Lines | 85 | DCD636 | Published | 2017-05-15 |  |  |  |  | SMB
Copy From | Sales | Using | Using Copy Options | 86 | DCD636 | Published | 2017-05-17 |  |  |  |  | SMB
Handling of Credit Controls | Sales | Using | Using Credit Controls | 87 | DCD711 | Published | 2017-06-29 |  |  |  |  | SMB
What's New Release No. 5.5 | What's New | Release No. 5.5 | What’s New 5.5 – BisTrack Cloud | 88 | DCD516 | Published | 2016-12-29
What's New Release No. 5.5 | What's New | Release No. 5.5 | What’s New 5.5 – BisTrack Cloud Signatures and Attachments | 89 | DCD525 | Published | 2017-02-07
What's New Release No. 5.5 | What's New | Release No. 5.5 | What’s New 5.5 - Competitor Price Capture | 90 | DCD530 | Published | 2017-01-25
What's New Release No. 5.5 | What's New | Release No. 5.5 | What’s New 5.5 - Payment Link | 91 | DCD517 | Published | 2017-03-31
What's New Release No. 5.5 | What's New | Release No. 5.5 | What’s New 5.5 – Using Pricing Planner | 92 | DCD531 | Published | 2017-03-13
What's New Release No. 5.5 | What's New | Release No. 5.5 | What’s New 5.5 - Tile Dashboards | 93 | DCD534 | Published | 2017-03-16
Master Table Setup Training - Product Groups | System Manager | Setup | Product Groups Overview | 94 | DCD661 | Published | 2017-05-22 |  |  |  |  | SMB
Master Table Setup Training - UOMs/UOM Rules | System Manager | Setup | Unit of Measure Overview | 95 | DCD679 | Published | 2017-05-31 |  |  |  |  | SMB
Master Table Setup Training - UOMs/UOM Rules | System Manager | Setup | System Managers Computer Option | 96 | DCD713 | Published | 2017-06-26 |  |  |  |  | SMB
Master Table Setup Training - UOMs/UOM Rules | System Manager | Setup | System Managers Document Controls | 97 | DCD715 | Published | 2017-06-23 |  |  |  |  | SMB
Overview | Advanced CRM | Overview | Overview | 98 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Release 4.0 enhancements
Setup | Advanced CRM | Setup | Setup | 99 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Calendar | Advanced CRM | Using | Calendar | 100 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Campaign Actions | Advanced CRM | Using | Campaign Actions | 101 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Campaigns | Advanced CRM | Using | Campaigns | 102 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Notepads | Advanced CRM | Using | Notepads | 103 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Opportunities | Advanced CRM | Using | Opportunities | 104 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Adding attachments to documents | BisTrack Basics | Tips & Tricks | Adding Attachments | 105 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Keyboard alternatives to using the mouse, system and product options to speed up order entry | BisTrack Basics | Tips & Tricks | Keyboard and System Shortcuts | 106 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
My Messages, Sending, Rules | BisTrack Basics | Using | Using Messages | 107 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B | Message Rules Instructions Manual
View tab, column widths, moving coloumns, sorting columns, Group By | BisTrack Basics | Using | Customizing Views | 108 | DCD961 | Published |  | 43006 |  |  | B | ECB video | HIGH
System option and using View Transaction Lock option | BisTrack Basics | Using | Viewing Transaction Locks | 109 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Release 3.3 enhancements
Logging in, navigating, cards, text fields | BT Cloud | Overview | BisTrack Cloud Overview | 110 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Entering quick orders, quotes, specials, find documents | BT Cloud | Transactions | BisTrack Cloud Sales Transactions | 111 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Look up, properties, views available | BT Cloud | Using | BisTrack Cloud Customers, Contacts and Products | 112 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Notepads, Advanced CRM, Business intelligence | BT Cloud | Using | BisTrack Cloud Other Functionality | 113 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
| BT Mobile | Overview | BisTrack Mobile Overview | 114 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
| BT Mobile | Overview | BisTrack Mobile Counting | 115 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | User Guide 2009
| BT Mobile | Overview | BisTrack Mobile Delivery | 116 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | User Guide 2009
| BT Mobile | Overview | BisTrack Mobile Order | 117 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | User Guide 2010
| BT Mobile | Overview | BisTrack Mobile Picking | 118 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | User Guide 2011
| BT Mobile | Overview | BisTrack Mobile Receipt | 119 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | User Guide 2013
| BT Mobile | Overview | BisTrack Mobile Stock | 120 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | User Guide 2007
Groupings, Properties, User Access, Schedules, Exporting | Business Intelligence | Overview | Reports Overview | 121 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Adding a Cube, Cube Properties, Data Cube Viewer | Business Intelligence | Using | Using Cubes | 122 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
| Business Intelligence |  | Dashboards | 123 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A | Likely more than 1 video; see Release videos
| Business Intelligence |  | Smart Views | 124 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A | Likely more than 1 video; see Release videos
Customer properties Contacts tab settings | Customers | Setup | Contacts Tab | 125 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B
Customer properties Accounts and Invoicing tabs settings | Customers | Setup | Accounts and Invoicing Tabs | 126 | DCD791 | Published |  | 2017-10-15 |  |  | B |  | HIGH
Customer properties Options and Notes tabs settings | Customers | Setup | Options and Notes Tabs | 127 | DCD1005 | Storyline in Progress |  | 2017-11-01 |  |  | B |  | HIGH
Customer properties Financial tab settings | Customers | Setup | Financial Tab | 128 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Notepad cases, creating notepads, notepad properties, messages | BisTrack Basics | Using | Using Notepads | 129 | DCD1020 | Storyboard in Progress |  | 2017-11-01 |  |  | I | Taiga PPT (6 Accounts) | HIGH
Notepad cases, creating notepads, notepad properties, messages | BisTrack Basics | Using | Using Notepad Cases | 130 | DCD1021 | Storyboard in Progress |  | 2017-11-01 |  |  | I | Taiga PPT (6 Accounts) | HIGH
Adding job accounts to a customers acct, Jobs view, Financials, Payments | Customers | Using | Customers with Job Accounts | 131 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Adding a new calendar year | Financial | Setup | Financial Calendar | 132 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Exporting financial data, financial support, report adjustment. | Financial | Using | Financial Exports | 133 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
| Installed Sales | Overview | Installed Sales Overview | 134 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 3.3 User Guide
Options, contracts, job accounts | Installed Sales | Setup | Installed Sales Setup | 135 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 3.3 User Guide
Shipping, Accrued AR, WIP, Credit Notes | Installed Sales | Transactions | Entering Installed Sales Transactions | 136 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 3.3 User Guide
Contracts setup | Installed Sales | Using | Adding Contracts | 137 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 3.3 User Guide
Complete Contract, views and reports | Installed Sales | Using | Completing a Contract | 138 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 3.3 User Guide
Kits types, adding to so, Kit Stock Enquiry | Kits | Overview | Kits Overview | 139 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Non-manufactured kits | Kits | Setup | Adding Non-Manufactured Kits | 140 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Likely more than 1 video
Manufactured kits | Kits | Setup | Adding Manufactured Kits | 141 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Likely more than 1 video, Release 4.5 Enhancements
Bill of Material Kits | Kits | Setup | Adding Bill of Material Kits | 142 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Adding a Non-manufactured kit to a sales order | Kits | Using | Using Non-Manufactured Kits | 143 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Adding a Manufactured kit to a sales order | Kits | Using | Using Manufactured Kits | 144 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Adding a Bill of Material Kit to a sales order | Kits | Using | Using Bill of Material Kits | 145 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Scanning options for Order Monitor | Order Monitor | Using | Using Batch Update | 146 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Release 3.2 enhancements
Views, adding notepads, options, maintenance | Planning | Using | My Calendar | 147 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I |  | HIGH
| Pricing | Maintenance | Maintaining Selling Price Rules | 148 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I | Pricing ppt and lesson plan | HIGH
Company and Branch prices, selling bands, Customer Price Profiles | Pricing | Overview | Pricing Basics | 149 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B | Pricing ppt and lesson plan
Rules by Price Profile, Price Band, Product Group and Price Group | Pricing | Overview | Selling Price Rules | 150 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B | Pricing ppt and lesson plan, Release 4.0 Enhancements
Rules by Price Profile and Product Group, Price Profile and Product | Pricing | Overview | Matrix Style Price Rules | 151 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I | Pricing ppt and lesson plan | HIGH
Review promotion types other than Sale Price | Pricing | Overview | Creating Promotions (Non-Sale Price) | 152 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Pricing ppt and lesson plan
| Pricing | Overview | Quantity Price Break Rules | 153 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I | Pricing ppt and lesson plan | HIGH
Purpose, Adding a rule, using on sales transaction | Pricing | Using | Using Selling Price Rules | 154 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I |  | HIGH
| Pricing | Using | Repricing a Sales Order to Price Rule or Profile | 155 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B | Pricing ppt and lesson plan | HIGH
Importing products from a spreadsheet | Products | Maintenance | Importing Products | 156 |  | No Storyboard Yet |  | 2017-10-30 |  |  | A |  | HIGH
Tally, Packs, Tally and Pack Calculator, Find Packs, Tagged and Non-Tagged Packs | Products | Overview | Lumber Tallys and Packs Overview | 157 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A | Taiga PPT (1a Sales), Release 4.5 Enhancements
Stock movement, stock buckets, stock information tabs, view allocations, view transactions | Products | Overview | Stock Information Overview | 158 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B | Taiga PPT (5 Stock Management)
Vendor managed inventory | Products | Overview | VMI Overview | 159 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT VMI Instruction (pdf in Taiga folder)
Vendor managed inventory | Products | Setup | VMI Setup | 160 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT VMI Instruction (pdf in Taiga folder)
Product properties Stock Options tab settings | Products | Setup | Stock Options Tab | 161 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B |  | HIGH
Product properties Branch Stock Options tab settings | Products | Setup | Branch Stock Options Tab | 162 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B |  | HIGH
Product properties Buying tab settings | Products | Setup | Buying Tab | 163 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B |  | HIGH
Product properties Selling tab settings | Products | Setup | Selling Tab | 164 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B |  | HIGH
Product properties Prices tab settings | Products | Setup | Prices Tab | 165 |  | No Storyboard Yet |  | 2017-10-30 |  |  | B |  | HIGH
Related products - Drywall example | Products | Tips & Tricks | Setting Related Products | 166 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Product Information tab | Products | Tips & Tricks | Product Information | 167 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Product Sets and Related Products | Products | Tips & Tricks | Related Products | 168 |  | No Storyboard Yet |  | 2017-11-15
Options button, Qty setting, Columns (RL products) | Products | Tips & Tricks | Finding Products | 169 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I |  | HIGH
Tally, Packs, entering onto Sales and Purchase documents, picking packs (tagged and non-tagged), pack adjustments | Products | Using | Using Lumber Tallys and Packs | 170 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A | Taiga PPT (1a Sales and 3 DD Picking, 1 Purchase Order, 2 Stock Receipts, 5 Stock Mgmnt)
Memo Quantity Input | Products | Using | Using Memo Quantity Input | 171 |  | No Storyboard Yet |  | 2017-11-15
Vendor managed inventory | Products | Using | Using VMI | 172 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT VMI Instruction (pdf in Taiga folder)
What are they, how to set up cost-controlled products, using on a PO, SR and SO. | Products | Using | Using Cost-Controlled Products | 173 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Overview, setup and browser | Purchasing | Overview | Suggested Order Overview | 174 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Suggested ordering line browser, editing, generating orders, schedule | Purchasing | Transactions | Generating Suggested Orders | 175 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Shipping and 3rd party freight | Purchasing | Transactions | Using 3rd Party Freight | 176 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Prorating freight over multiple POs/SRs | Purchasing | Using | Using Additional Cost/Charge Proration | 177 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Taiga PPT (2 Freight)
| Purchasing | Using | Stock Receipts in Advance | 178 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B | Taiga PPT (2 Stock Receipts
Modifying costs and quanties on a SR after it has been received. | Purchasing | Using | Stock Receipt Adjustments | 179 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Taiga PPT (2 Stock Receipts
Incoming, Changing the incoming documents | Purchasing | Using | eBusiness for Purchasing | 180 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT EDI Operational Instructions Manual
| Purchasing | Using | Call Off Purchase Orders | 181 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Overhead suppliers and entering a OH PO, Receiving | Purchasing | Using | Using Overhead Purchase Orders | 182 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Add New based on Sales and Usage | Purchasing | Using | Adding New Suggested Orders | 183 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A | Release 3.3, 4.0 enhancements
Buying Price Rules, VMI Rules, Supplier Retrospective Discounts, Supplier Support Agreements | Purchasing | Using | Buying Price Rules | 184 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Added Value Operations - Overview, Added Value Operations - Setup | Sales | Overview | Added Value Operations (AVOs) Overview | 185 |  | No Storyboard Yet |  | 2017-11-15
Customer Loyalty Programs - Overview, Customer Loyalty Programs - Setup | Sales | Overview | Customer Loyalty Programs Overview | 186 |  | No Storyboard Yet |  | 2017-11-15
Overview and entering a template order, convert to sales order | Sales | Transactions | Using Template Orders | 187 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Scheduling AVOs, use of machines and production times | Sales | Transactions | AVO Scheduling | 188 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Release 4.0 enhancements
Added Value Operations on a Sales Document | Sales | Using | Using Added Value Operations (AVOs) | 189 |  | No Storyboard Yet |  | 2017-11-15
Customer Loyalty Programs - Process | Sales | Using | Using Customer Loyalty Programs | 190 |  | No Storyboard Yet |  | 2017-11-15
Reservations | Sales | Using | Using Reservations | 191 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Entering and saving a bank reconciliation | Sales | Using | Creating Bank Reconciliation Deposit | 192 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Taiga PPT (6 Accounts)
Outgoing, Resending the outgoing documents, troubleshooting | Sales | Using | eBusiness for Selling | 193 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Taiga PPT (6 EDI) BT EDI Operational Instructions Manual
System options to force verify of photo/signature on contact name verification, limit contacts to those based at delivery address, display order contact from customer/customer delivery address. | Sales | Using | Authorized Contact Verification | 194 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Schedule tab | Sales | Using | Call Off Orders Scheduling | 195 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Overview, setup and transactions using a cash account balance | Sales | Using | Using Cash Account Balances | 196 |  | No Storyboard Yet |  | 2017-10-30 |  |  | I | BT 4.5 Release Notes/Video | HIGH
Overview, set up and entering a cash refund requiring manager authorization | Sales | Using | Manager Authorization on Cash Refunds | 197 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B | BT 5.0 Release Notes/Video, ECB
Overview, setup and using on transactions | Sales | Using | Gift Cards | 198 |  | No Storyboard Yet |  | 2017-10-30 |  |  | S |  | HIGH
Options for using Price Enquiry window | Sales | Using | Using Price Enquiry | 199 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Adding a Price List | Sales | Using | Using Price Lists | 200 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Quick Products setup and using in order entry. | Sales | Using | Quick Products | 201 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Release 5.5 enhancements
Setting up Auto Delivery Charges, entering on a sales or purchasing transaction. | Sales/Purchasing | Using | Automatic Delivery Charges | 202 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | Release 3.0 enhancements
Overview and setup | Stock Management | Overview | Product Batches Overview | 203 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 4.5 Release Notes/Video/PDF
Overview and setup | Stock Management | Overview | Scan Track Overview | 204 |  | No Storyboard Yet |  | 2017-10-30 |  |  | S |  | HIGH
| Stock Management | Overview | Stock Valuation Overview | 205 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Ticketed stock count | Stock Management | Overview | Ticketed Stock Counting Overview | 206 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Transactions using Product Batches | Stock Management | Using | Using Product Batches | 207 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | BT 4.5 Release Notes/Video/PDF
Transactions using Product Batches | Stock Management | Using | Using Scan Track | 208 |  | No Storyboard Yet |  | 2017-10-30 |  |  | S |  | HIGH
New stock valuation, reports Inventory Reconciliation Report | Stock Management | Using | Using Stock Valuations | 209 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Ticketed stock count | Stock Management | Using | Using Ticketed Stock Counting | 210 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
| Stock Management | Views | Stock Reports | 211 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
Supplier properties Contacts tab settings | Suppliers | Setup | Contacts Tab | 212 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Supplier properties Options and Purchasing tabs settings | Suppliers | Setup | Options and Purchasing Tabs | 213 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Supplier properties Notes and Notepad tabs settings | Suppliers | Setup | Notes and Notepad Tabs | 214 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
System manager setup and using | Suppliers | Using | Automatic Average Cost Adjustment Rules | 215 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
System Options settings, Browser window | System Manager | Overview | eBusiness Overview | 216 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Taiga PPT (6 EDI), BT EDI Operational Instructions Manual
| System Manager | Overview | Profile Designer Overview | 217 |  | No Storyboard Yet |  | 2017-10-30 |  |  | A |  | HIGH
Divisions, Branches, Counties, Countries, Departments | System Manager | Setup | Corporate Settings | 218 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I | BT 3.2 (V &PPT) - Consolidate Lines Only
| System Manager | Using | Using Profile Designer | 219 |  | No Storyboard Yet |  | 2017-10-30 |  |  | A | Likely more than 1 video | HIGH
Audit setup and view audit log | System Manager | Using | Using Audit Information | 220 |  | No Storyboard Yet |  | 2017-11-15 |  |  | A
Overview | Web Track | Overview | Web Track Overview | 221 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Setting up to use Web Track. | Web Track | Setup | Web Track Setup | 222 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S
Transactions in Web Track | Web Track | Using | Using Web Track | 223 |  | No Storyboard Yet |  | 2017-11-15 |  |  | S | Likely more than 1 video
| Works Orders | Overview | BisTrack Works Orders Overview | 224 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
AVOs, External, Work Flows, Costing | Works Orders | Transactions | Works Orders Processes and Costing | 225 |  | No Storyboard Yet |  | 2017-11-15 |  |  | I
For Cutting, Treating, Millwork | Works Orders | Using | Using Works Orders | 226 |  | No Storyboard Yet |  | 2017-11-15 |  |  | B
Machines, Machine Groups, Add work to schedule, views, options | Works Orders | Using | Using Schedules | 227 |  | No Storyboard Yet |  | 2017-11-30 |  |  | A | Release 4.5 Enhancements
| System Manager | Setup | Setup Delivery Areas | 228 |  | No Storyboard Yet |  | 2017-11-30
| System Manager | Setup | Setup Customer Types | 229 |  | No Storyboard Yet |  | 2017-10-30 |  |  |  |  | HIGH
| System Manager | Setup | Setup Customer Payment terms | 230 |  | No Storyboard Yet |  | 2017-10-30 |  |  |  |  | HIGH
| System Manager | Setup | Setup Customer Price Profiles | 231 |  | No Storyboard Yet |  | 2017-10-30 |  |  |  |  | HIGH
| System Manager | Setup | Setup Sales Reps | 232 |  | No Storyboard Yet |  | 2017-10-30 |  |  |  |  | HIGH
|  |  | BisTrack Customer Loyalty Game | 233 | DCD928 | Published | 2017-09-19
| Sales | Tips & Tricks | Adding GL codes to MOLT’s AVO’s and Reason Codes | 234 |  | No Storyboard Yet |  | 2017-11-30 |  |  |  | Tammy Boles | HIGH
| Financial | Setup | Financial Interface | 235 |  | No Storyboard Yet |  | 2017-11-30 |  |  |  | Tammy Boles | HIGH
| Financial | Reports | Financial Export Summary | 236 |  | No Storyboard Yet |  | 2017-11-30 |  |  |  | Tammy Boles | HIGH

## Proposed Offerings
Topic(s) | Category | Content Currently Avail? | Course Title | Misc Notes/Concerns
| Accounts Payable | NO | Accounts Payable Reports
| Accounts Receivable | NO | Accounts Receivable Reports
| Sales | NO | Add Timber Pack
| CRM | Video/User Guide | Advanced CRM - Calendar
| CRM | Video/User Guide | Advanced CRM - Campaign Actions
| CRM | Video/User Guide | Advanced CRM - Campaigns
Notepad types and statuses | CRM | Video/User Guide | Advanced CRM - Notepads
| CRM | Video/User Guide | Advanced CRM - Opportunities
| CRM | Video/User Guide | Advanced CRM - Overview
| Dispatch and Delivery | BT 3.1 (V, PPT) | Advanced Picking - orders for Collection
| Dispatch and Delivery | BT 3.1 (V, PPT) | Advanced Picking - orders for Delivery
| Purchasing & Receiving | BT 3.1 (V, PPT) | Allocating Purchase Order Numbers and Copy Purchase Orders
| Purchasing & Receiving | BT 3.1 (V, PPT) | Allocating Stock from a Purchase Order to a Sales Order
| Sales | BT 3.2 Release Notes/Video | Authorized Contact Verification
| Suppliers | NO | Automatic Average Cost Adjustment Rules
| Stock Management | BT 3.1 (V, PPT) | Average Cost Adjustment
| System Manager | NO | Bank Accounts
| Sales | BT 4.5 User Guide | BisTrack Cloud | Analysis required to determine scope.
| Sales | BT 4.0 Release Notes/Video | BisTrack Display - Overview
| Sales | BT 4.0 Release Notes/Video | BisTrack Display - Process
| Sales | BT 4.0 Release Notes/Video | BisTrack Display - Setup
| Stock Management | User Guide 2009 | BisTrack Mobile - Counting | Analysis required to determine scope.
| Stock Management | User Guide 2009 | BisTrack Mobile - Delivery | Analysis required to determine scope.
| Stock Management | User Guide 2010 | BisTrack Mobile - Order | Analysis required to determine scope.
| Stock Management | User Guide 2011 | BisTrack Mobile - Picking | Analysis required to determine scope.
| Stock Management | User Guide 2013 | BisTrack Mobile - Receipt | Analysis required to determine scope.
| Stock Management | User Guide 2007 | BisTrack Mobile - Stock | Analysis required to determine scope.
| Sales | BT 3.2 (V &PPT) | Call Off Orders
| Sales | BT 3.2 (V &PPT) | Call Off Orders Schedules
| Purchasing & Receiving | BT 3.1 (V, PPT) | Call Off Purchase Orders
| Sales | BT 4.5 Release Notes/Video | Cash Account Balances - Overview and Setup
| Sales | BT 4.5 Release Notes/Video | Cash Account Balances - Process
| Sales | BT 5.0 Release Notes/Video, ECB | Cash Refunds with Manager Authorization - Overview and Setup
| Sales | BT 5.0 Release Notes/Video, ECB | Cash Refunds with Manager Authorization - Process
Consolidate All within Sections, Consolidate within Selected Sections | Sales | BT 3.2 (V &PPT) - Consolidate Lines Only | Consolidate Lines and Sections
Divisions, Branches, Counties, Countries, Departments | System Manager | NO | Corporate Settings
| Sales |  | Create Bank Reconciliation Deposit
| Sales | BT 4.5 Release Notes/Video | Credit and Rebill
| Business Intelligence | NO | Cubes | Analysis required to determine scope.
| System Manager | NO | Currencies
| Customers | BT 3.0 PPT | Customer - Import Spreadsheet and Importing
Coupons and Levels | Customers | BT 5.0 Release Notes/Video | Customer Loyalty Programs
| Sales | BT 5.0 Release Notes/Video | Customer Loyalty Programs - Overview
| Sales | BT 5.0 Release Notes/Video | Customer Loyalty Programs - Process
| Sales | BT 5.0 Release Notes/Video | Customer Loyalty Programs - Setup
| BisTrack Basics | BT 3.3 V, ECB | Customizing Views
| Business Intelligence | NO | Dashboards | Analysis required to determine scope.
| Dispatch and Delivery | NO | Delivery Areas, Times and Dates Required
Include information on Auto Text | Sales | BT 3.2 (V &PPT) | Delivery Instructions and Document Notes
| Dispatch and Delivery | BT 3.1 (V, PPT) | Delivery Planner Views
| Dispatch and Delivery | BT 3.1 (V, PPT) | Dispatch and Delivery "My Options"
| Dispatch and Delivery | BT 3.1 (V, PPT) | Dispatching a Delivery
| System Manager | BT 2.8 User Guide | Document Control | Analysis required to determine scope.
Changing the incoming documents, Resending the outgoing documents, Troubleshooting issues with documents | eBusiness | NO | EDI | Analysis required to determine scope.
|  | Various User Guides. | Electronic Payment Processing (Debit, Credit, Gift Cards) | Will require a variety of videos depending on method being used (i.e. Shift4, Ingenico, etc.)
| Business Intelligence | NO | Email Templates | Analysis required to determine scope.
| Sales | BT 3.2 (V &PPT) | Enable/Disable Delivery Charges
| Stock Management | NO | Entering a Works Order - Cutting Operation
| Stock Management | NO | Entering a Works Order - Manufactured Goods (Doors/Windows)
| Stock Management | NO | Entering a Works Order - Millwork
| Stock Management | BT 3.1 (V, PPT) | Entering a Works Order - Treating
| Stock Management | BT 3.1 (V, PPT) | Entering a Works Order (work done elsewhere)
| Stock Management | BT 3.1 (V, PPT) | Entering a Works Order from a Sales Order
From Overhead and Direct AP invoices, Debit Notes. | Accounts Payable | BT 3.1 (V, PPT) | Entering Other Supplier Credit Notes
| Accounts Payable | BT 3.1 (V, PPT) | Entering Supplier Credit Notes from Supplier Return
| Accounts Payable | BT 3.1 (V, PPT) | Entering Supplier Credit Notes without Supplier Return
My Options, Change Password, Change Branch | BisTrack Basics | NO | File Tab
| Financial | NO | Financial Calendar Setup
| Financial | NO | Financial Interface Setup to GP
Reports used for GL reconciliation purposes. | Financial | BT 2.7 Financial Reconciliation Guide | Financial Reports | Analysis required to determine scope.
| Sales | BT 3.2 (V &PPT) | Find Cash Account Order
| Purchasing & Receiving | NO | Finding Purchase Orders
| Purchasing & Receiving | NO | Finding Stock Receipts
| System Manager | NO | Form Designer | Analysis required to determine scope.
| Sales | BT 4.5 Release Notes/Video | Generate Supplier Return from Credit Note/Cash Refund
UOMs, Each products | Sales | BT 3.2 (V &PPT) | Generic Products on a Sales Document
Include Direction Source (System Manager - General View option) | Dispatch and Delivery | NO | Get Directions
| Sales | Release Notes | Gift Cards - Overview
| Sales | Release Notes | Gift Cards - Process
| Sales | Release Notes | Gift Cards - Setup
| Financial | NO | GL Code Validation
| Financial | NO | GL Codes
| Sales | BT 3.2 (V &PPT) | Insert Product, Resort Order, Copy Line
| Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales - Overview
System Options, Sales Tax, MOLTs, Schedules | Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales - Setup
| Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales - Setup Contracts
| Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales - Setup Job Accounts
Find Documents, Related Documents, Contract Invoicing Report, Balancing Report | Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales - Views and Reports
Shipping and Billing Transactions | Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales Transactions - Accrued AR
| Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales Transactions - Credit Notes
Shipping and Billing Transactions | Sales | BT 3.3 User Guide/Release Notes/PPT | Installed Sales Transactions - Work-in-Progress
| Accounts Payable | BT 3.1 (V, PPT) | Introducing Accounts Payable
Customer Financials and Statistics tab of Customer Properties and associated views from buttons. | Accounts Receivable | BT 3.1 (V, PPT) | Introducing Accounts Receivable
| Dispatch and Delivery | BT 3.1 (V, PPT) | Introducing Dispatch and Delivery (aka Journey Planner )
Order status and processing cycle. | Dispatch and Delivery | BT 3.1 (V, PPT) | Introducing Order Monitor
| Stock Management | NO | Inventory Reporting
| Kits | BT 5.0 User Guide/PPT/Release Notes and Video | Kits - Manufactured | Analysis required to determine scope. Estimate 8 to 10 videos.
| Kits | BT 2.8 User Guide/Release Notes and Videos | Kits - Non Manufactured | Analysis required to determine scope. Estimate 4 to 6 videos.
| Kits | ?? | Kits - Purchased | Not sure of any existing material related to this method. Analysis required to determine scope.
| Purchasing & Receiving | BT 3.1 (V, PPT) | Label Printing
| Sales | BT 3.2 (V &PPT) | Line Notes, Instructions, Text Lines
| Suppliers | BT 3.0 PPT | Link to GP Setup
UOMs, Sheet, Random Length, Parent/Child, Linear Foot, etc. | Sales | BT 3.2 (V &PPT) | Lumber Products on a Sales Document
| Planning | NO | Machines and Machine Groups
Supplier Invoices on Hold, Messages to Purchasing Agents, Monitoring Invoices | Accounts Payable | BT 3.1 (V, PPT) | Managing Supplier Invoices
| Pricing | BT 3.0 PPT | Matrix Style Pricing
| Purchasing & Receiving | BT 3.1 (V, PPT) | Merging Purchase Orders
| BisTrack Basics | NO | Messages (My Messages)
|  | BT 2.5 User Guide | Messaging | Analysis required to determine scope.
| System Manager | NO | My Options
| Planning | NO | My Schedule
Quick Entry, Qty and Price, Qty Only | Sales | BT 3.3 Release Notes/Video | Options for entering Qty and Price
Notes, Supplier, Shipping, Status Summary, Transport Booking | Purchasing & Receiving | BT 3.1 (V, PPT) | Other Tabs for Entering Purchase Orders
|  | BT 4.0 User Guide (Outlook 2013) | Outlook Integration | Analysis required to determine scope.
| Purchasing & Receiving | BT 3.1 (V, PPT) | Overhead Purchase Orders - Overview
| Purchasing & Receiving | BT 3.1 (V, PPT) | Overhead Purchase Orders - Process
| Purchasing & Receiving | BT 3.1 (V, PPT) | Overhead Purchase Orders - Setup
Include Allocating a Sales Order number | Sales | ECB, BT 3.2 (V &PPT) | Parking and Order
| System Manager | NO | Payment Methods
| Dispatch and Delivery | BT 3.1 (V, PPT) | Preparing a Delivery
| Sales | BT 3.2 (V &PPT) | Price Bands on a Sales Document
| Sales | BT 3.2 (V &PPT) | Price Bands Overview and Setup
| Sales | BT 3.2 (V &PPT) | Price Calculation Tab, History and Quotes
| Sales | BT 3.2 (V &PPT) | Price Enquiry
| Pricing | BT 3.0 PPT | Price Group Rules
Selling Price, Total Price, Profit, Margin %, Selling Price UOM, Line Discounts, Showing Cost and Margin Info | Sales | BT 3.2 (V &PPT) | Price Negotiation Tab
Introduction Selling and Buying Price Rules | Pricing | NO | Pricing - Overview
Lump sum pricing, manual price lines, negotiation discounts | Sales | BT 3.2 (V &PPT) | Pricing Options 1
Price profiles, price rules, restore calculated price | Sales | BT 3.2 (V &PPT) | Pricing Options 2
| Sales | NO | Print Labels
| Products | BT 4.5 Release Notes/Video | Product Batches - Overview and Setup
| Products | BT 4.5 Release Notes/Video | Product Batches - Process
| Products | BT 3.0 PPT | Products - Import Spreadsheet and Importing
| Products | BT 3.0 PPT | Products - Overview
| System Manager | NO | Profile Designer | Analysis required to determine scope.
| Pricing | BT 3.0 PPT | Promotions
| Purchasing & Receiving | BT 3.1 (V, PPT) | Purchasing Cycle and Supplier Invoicing
| Purchasing & Receiving | BT 3.1 (V, PPT) | Purchasing Functions Linked to Sales - Overview
| Purchasing & Receiving | NO | Purchasing Reports
| Pricing | BT 3.0 PPT | Quantity Breaks
| Purchasing & Receiving | BT 3.1 (V, PPT) | Receiving a Purchase Order in Advance
| Purchasing & Receiving | NO | Receiving Reports
|  | User Guide 2009 | Report Server | Analysis required to determine scope.
| Pricing | BT 3.0 PPT | Repricing Sales Orders and Maintaining Pricing
| Sales | BT 3.2 (V &PPT) | Reservations
| Sales | NO | Sales Reps and Sales Areas
|  | NO | Scan Track | Analysis required to determine scope.
| Planning | Release Notes/Videos? | Scheduling | Analysis required to determine scope.
| Sales | BT 3.2 (V &PPT) | Sections and Summary Lines
| Pricing | NO | Selling Price Changes
| Business Intelligence | NO | Smart Views | Analysis required to determine scope.
| Pricing | BT 3.0 PPT | Special Prices
| Business Intelligence | NO | SQL Reporting Services | Analysis required to determine scope.
| Business Intelligence | NO | Standard Reports | Analysis required to determine scope.
| Dispatch and Delivery | BT 3.1 (V, PPT) | Starting and Completing a Delivery
| Stock Management | BT 3.1 (V, PPT) | Stock Counting - Overview
| Stock Management | BT 3.1 (V, PPT) | Stock Counting - Process
| Stock Management | BT 3.1 (V, PPT) | Stock Counting - Setup
| Purchasing & Receiving | BT 3.1 (V, PPT) | Stock Receipt Adjustments
Generating a stock valuation | Stock Management | NO | Stock Valuation - New Stock Valuation
| Stock Management | BT 3.1 (V, PPT) | Stock Valuation - Overview
Stock Valuation Reconciliation, troubleshooting discrepancies. | Stock Management | NO | Stock Valuation - Reports
| Sales | NO | Substitute Product
| Purchasing & Receiving | Release Notes | Suggested Order Auto Schedule
| Purchasing & Receiving | BT 3.1 (V, PPT) | Suggested Order Batches Browser
| Purchasing & Receiving | BT 3.1 (V, PPT) | Suggested Order Line Browser for Editing Suggestions
Weighting | Purchasing & Receiving | BT 3.1 (V, PPT) | Suggested Ordering - Add New and Generate - Based on Sales
Weighting | Purchasing & Receiving | BT 3.1 (V, PPT) | Suggested Ordering - Add New and Generate - Based on Usage
Methods available and deciding on appropriate one to use. | Purchasing & Receiving | BT 3.1 (V, PPT) | Suggested Ordering - Overview
| Purchasing & Receiving | BT 3.1 (V, PPT) | Suggested Ordering - Setup
| Accounts Payable | BT 3.1 (V, PPT) | Supplier Invoice Browser
| Accounts Payable | BT 3.1 (V, PPT) | Supplier Invoices with Variances
| System Manager | NO | System Options | Analysis required to determine scope.
| Sales | BT 3.2 (V &PPT) | Template Orders
| Business Intelligence | NO | Templates | Analysis required to determine scope.
| Stock Management | BT 3.1 (V, PPT) | Ticketed Stock Counting - Overview
| Stock Management | BT 3.1 (V, PPT) | Ticketed Stock Counting - Process
| Stock Management | BT 3.1 (V, PPT) | Ticketed Stock Counting - Setup
|  | User Guide 2008 | Transport Booking/3rd Party Freight | Analysis required to determine scope.
Order Statuses, Setting Criteria, Viewing Results, Selecting for Collection/Delivery. | Dispatch and Delivery | BT 3.1 (V, PPT) | Using Order Monitor
| Dispatch and Delivery | BT 3.1 (V, PPT) | Vehicles and Drivers - Setup
| Stock Management | NO | View Packs
| Stock Management | BT 3.1 (V, PPT) | View Stock Allocations
| Stock Management | BT 3.1 (V, PPT) | View Stock Transactions
| Sales | NO | Web Track | Analysis required to determine scope.
| Stock Management | BT 3.1 (V, PPT) | Works Orders - Overview

## ABRM
Agenda Title | AR CLERK | AR MANAGER | AP CLERK | AP MANAGER | ASST. STORE MANAGER | CONTRACTOR SALES | DISPATCH/WAREHOUSE MANAGER | GL CLERK | GL MANAGER | INVENTORY CLERK | INVENTORY MANAGER | IT MANAGER | SYSTEM ADMINISTRATOR | OWNER | PAYROLL MANAGER | PURCHASING CLERK | PURCHASING MANAGER | POS CLERK / CASHIER | POS HEAD CLERK / CASHIER | POS MANAGER | RECEIVING CLERK | RECEIVING MANAGER | STORE MANAGER
Epicor Learning Center Learner Agenda | X | X | X | X | X | X | X | X | X | X |  |  |  |  | X | X | X | X | X | X | X | X | X
Epicor Learning Center Administrators Agenda | [11 empty] | X | X | X
Getting Started with BisTrack (Administrator) | [12 empty] | X
Getting Started with BisTrack (Learner) | X | X | X | X | X | X | X | X | X | X | X | X |  | X | X | X | X | X | X | X | X | X | X
BisTrack System Setup |  | X |  | X | [6 empty] | X |  | X |  |  |  | X | [5 empty] | X
BisTrack Customers, Suppliers and Products |  | X |  | X | [6 empty] | X |  | X |  |  |  | X | [5 empty] | X
BisTrack Sales Fundamentals |  |  |  | X |  | X | X |  |  |  | X |  | X |  |  |  | X | X | X | X |  |  | X
BisTrack Additional Sales Functions | [5 empty] | X | X | [5 empty] | X | [9 empty] | X
BisTrack Purchasing & Receiving Processes |  |  |  | X | [6 empty] | X |  | X |  |  |  | X |  |  |  |  | X | X
BisTrack Accounts Payable Functions |  |  |  | X | [8 empty] | X | [9 empty] | X
BisTrack Accounts Receivable Functions |  | X | [10 empty] | X | [9 empty] | X
BisTrack Stock Management Functions | [10 empty] | X |  | X | [9 empty] | X
Basic BisTrack Dispatch and Delivery Functions | [6 empty] | X | [5 empty] | X | [9 empty] | X
Additional BisTrack Dispatch and Delivery Functions | [6 empty] | X | [5 empty] | X | [9 empty] | X